## Appendix 6.2 (hidden)
Typical information required | Select | Define | Exceute | Operation | Non-operation
Operations and Maintenance philosophy | E | E | E | E | E
Process and Chemistry Descriptions | E | E | E | E | E
Process Control Narrative | D | E | E | E | E
Reactive Hazard (if applicable) | E | E | E | E | E
Material Safety Data Sheet | E | E | E | E | E
Plot Plan | E | E | E | E | E
General Equipment Arrangements & Elevations | - | E | E | E | E
Electrical/ Hazardous Area Classification Drawings | - | E | E | E | E
Heat and Mass balances | D | E | E | E | E
Process Flow Scheme (or PFD) and Utility Flow Scheme (UFS) | E | E | E | E | E
Process Engineering Flow Scheme and legend sheets (or P&IDs and UEFS) | D | D | E | E | E
Line lists for piping & process equipment | - | E | E | E | E
Equipment data sheet | - | D | E | E | E
Process Safeguarding Flow Scheme | D | E | E | E | E
Cause and Effect Diagrams | - | E | E | E | E
SIL Study report | - | - | E | E | E
Control valve turndown, RV, trip and alarm settings | - | E | E | E | E
Latest construction/ as-built drawings | - | - | E | E | E
Previous HAZID/HAZOP reports and Close Outs report | - | D | E | E | E
Details of change since last Process hazard analysis (PHA) | - | D | E | E | E
Other safety studies, such as Bow-tie analysis | - | - | D | E | E

## Table A6.2-3
Table A6.2-3 P&ID readiness checklist for HAZOP Study
|  | MoC / Project title : | [5 empty] | Evaluation Date :
No. | Checklist Item |  | Critical | Purpose / What to Check | Review |  |  | Remark
[5 empty] | YES | NO | Not Related
1 | Latest revision issued & controlled Old revision used → missing design changes, leading to irrelevant or incorrect discussions. |  | YES | Ensure HAZOP uses the most current approved revision.
2 | Scope completeness (systems, subsystems, boundaries) Parts of process omitted → hazards not identified. |  | YES | Ensure that P&ID available for all relate scope of HAZOP. (PFD is not sufficient for HAZOP Study) P&ID show the scope corrPrevents omission of units or tie-ins.
3 | Equipment tags complete & consistent Facilitator/team wastes time clarifying missing/duplicated equipment tags. |  | YES | Ensures all equipment is identified - no missing of equipment - no incorrect equipment sequence - no duplicated tag / incorrect tag
4 | Line identification Inability to distinguish between critical and minor lines during hazard scenarios. |  | YES | - All line complete with correct direction - Line identification complete (number, size, service, class etc.)
5 | Instrumentation (Indicators, transmitters, alarms) Risk of overlooking failure of unmarked instruments, incomplete/incorrect hazard identification, missing of barrier identification. |  | YES | Ensure that all instrumentation present correctly - no missing instrument - correct instrumentation symbol - no missing/incorrect of alarm of alarm indication (e.g. L, LL, H, HH)
6 | Control loops & Interlocks Hazardous deviations missed leading to incomplete/incorrect hazard identification, missing of barrier identification and incorrect risk ranking. |  | YES | Ensure that all control and interlock is present correctly. - no missing control / interlock loop - clear concention to the action element. Note Indication connection between sensor to final element may be not line-connection which depend on plant. - Fail position of valve
7 | Safety devices (PSVs, rupture discs, etc.) Relief scenarios cannot be validated; potential overpressure risk ignored. |  | YES | Ensure that the relief device is present correctly. - no missing pressure relief device. - correct destination - set pressure is available correctly
8 | Tie-ins location Hazards at interface (wrong pressure/contamination) overlooked. |  | YES | - Tie-ins location is identified - Isolation configuration follow reference specification
9 | Isolation devices shown (block valves, blinds) Potential misundersatanding operation sence leading to improper/incorrect/incomplete develop conseqeunce and Inability to evaluate isolation adequacy for maintenance/emergency |  | YES | Block valves, Blinds, Indication for normal close and/or nomal open is present correclty and clearly understanding the operation sence.
10 | Consistency across multiple drawings Time wasted reconciling discrepancies between sheets. |  | YES | Ensures that symbol for continuation drawing is present with correct detial.
11 | Legend/symbols available Misinterpretation of instruments/valves (e.g., MOV vs. manual). |  | - | Ensure that legend and symbol is present, applied correctly and align with plant basis.
12 | Notes and references Hazards from special conditions (e.g., thermal expansion) overlooked. |  | - | Notes are available. - no present note without explanation - no duplicate note - note present with correct location
13 | Consistency with PFD, line list, equipment list Inconsistencies → confusion and wasted HAZOP time. |  | - | Ensure that information in P&ID consistance with information in PFD.
Conclusion by HAZOP Coodinator |  |  |  |  | YES | NO | Remark
All item are available without deficiency or those deficiency can be solved such as correct/provide information with hand mark up?