## Cover Page
PRELIMINARY HAZOP STUDY — WORKSHEET EXPORT
Plant | PTT Phenol Train II (PPCL), Map Ta Phut, Thailand
Section / Unit | CDN — Concentration, Decomposition, Neutralization
Node | CDN-N02 (engineer P&ID markup: "Node 23-02")
Node description | Preflash Column Feed-Heating / Steam-Condensate Circuit
Equipment in node | E-2302A/B, E-2303, D-2308, P-2308A/B
P&ID drawings | 14780-8120-25-23-0005, -0005A (primary); -0004, -0007 (boundary crossings)
Licensor / Engineer | UOP (Honeywell) / POSCO Engineering
PHA No. | TBD (assign in e-PHA system)
HAZOP purpose | Standalone CDN section HAZOP (process safety study)
Risk basis | PTT GC RAM W-(Q-MP)-002 R2; Economic category = BU (confirmed for PPCL)
Revision / Date | Rev. A (Preliminary) — worksheet 2026-06-17; export 2026-06-18
Report status | PRELIMINARY — DESKTOP FIRST-PASS (not team-validated/approved)
Prepared by | Process Expert Assistant (machine-generated, wiki-grounded)
Reviewed / Approved by | TBD — HAZOP Leader (pending facilitated workshop)
DISCLAIMER | Preliminary aid to the HAZOP workshop. Causes, consequences, safeguard adequacy, risk rankings and recommendations are provisional and MUST be reviewed and finalized by the qualified HAZOP team per GC procedure P-(Q-MP)-OEMS-005. Not an approved HAZOP record; not a basis for design/operating decisions until approved.

## HAZOP Information
HAZOP INFORMATION
Project / MOC No. | Standalone CDN HAZOP (not MOC-driven)
Project title | PTT Phenol Train II — CDN Section HAZOP
Plant | PTT Phenol Train II (PPCL)
Unit / Facility | CDN — Concentration sub-section
HAZOP purpose | Process safety study (standalone)
HAZOP scope (this export) | Node CDN-N02 only — Preflash Column feed-heating / steam-condensate circuit
Process description | Heats CHP-containing oxidate (~22.6 wt% CHP) from OXI: heat recovery in E-2302A/B (oxidate vs hot OXI recirculate), steam trim in E-2303 (SC1.5), feed to V-2301; E-2303 condensate collected in D-2308 and returned by P-2308A/B.
Key chemicals | Cumene Hydroperoxide (CHP, decomposition onset ~80 C, SADT 60-80 C), cumene, phenol, acetone; SC1.5 steam/condensate (utility).
Governing hazard | Over-temperature of CHP-containing oxidate above ~80 C -> autocatalytic exothermic decomposition -> overpressure/rupture, fire/explosion.
Methodology | GC 9-step HAZOP, parameter-first, full-record (SG-(Q-MP)-014 R3).
Risk matrix | W-(Q-MP)-002 R2 (5x5 PEES). Severity fixed between initial/mitigated; only Likelihood changes with safeguards.
Economic category | BU (confirmed for PPCL 2026-06-17): Extreme>=100M; High 10-<100M; Medium 1-<10M; Low 0.1-<1M; Very Low <0.1M THB.
IPL credit | SG-(Q-MP)-014 Tables 6.4-6.6. SIL1 = -1 level; SIL2 = -2. Fire protection / emergency response NOT credited.
Anti-bias | No previous Phenol/CDN HAZOP report referenced. O-P3 example used as layout reference only.
Assumptions | Boundaries per engineer markup (confirmed 2026-06-17). Preliminary desktop pass; team to validate.
General notes | Acceptable risk (GC) = Low or Very Low. Mitigated risk >= Medium requires a recommendation.

## WorkSheet Index
Node No. | Node Description | Design Intention | Design / Operating Condition | Colour code | Related Drawing No. | Status
CDN-N02 (markup "Node 23-02") | Preflash Column feed-heating / steam-condensate circuit (E-2302A/B, E-2303, D-2308, P-2308A/B) | Heat oxidate feed to Preflash Column target temp: recover heat in E-2302A/B, trim with SC1.5 steam in E-2303, deliver to V-2301; collect/return E-2303 condensate. | Process: oxidate ~82-83 C, ~8 kg/cm2g (CHP ~22.6 wt%). E-2303 tube SC1.5 steam ~120-133 C (des 7 kg/cm2g). D-2308 0.9 kg/cm2g / 117 C. E-2302 tube des 12 kg/cm2g. | Yellow | 0005 / 0005A (+0004, 0007) | PRELIMINARY DRAFT 2026-06-17

## WorkSheet CDN-N02
[5 empty] | WITHOUT SAFEGUARD (Initial Risk) | [5 empty] | EXISTING SAFEGUARD |  |  | WITH EXISTING SAFEGUARD (Mitigated Risk) | [6 empty] | AFTER RECOMMENDATION COMP. (fill at close-out)
Ref | Parameter | Deviation | Possible Cause | Potential Consequence | L | P | En | Ec | S | RR | Existing Safeguard | IL/ESD | IPL | L | P | En | Ec | S | RR | Recommendation | L | P | En | Ec | S | RR
1.1.1 | Flow | No / Low Flow | Loss of oxidate feed (X-2302A/B filter plugging / OXI feed-pump trip / spurious UXV-0401 closure) with SC1.5 steam still on | Stagnant CHP oxidate locally overheats in E-2303/E-2302 above ~80 C -> autocatalytic decomposition -> heat + O2 -> overpressure, exchanger/line rupture -> LOPC of hot CHP -> fire/explosion, potential multiple fatalities | 4 | 5 | 4 | 5 | 4 | Extreme | FXSLL-0401A/B/C (2oo3, SIL 1) -> UC-2301 closes UXV-0401 feed + UXV-0501/0502 SC1.5 steam (C&E Cause 1) | Yes | 1 | 2 | 5 | 4 | 5 | 4 | Medium | R-001
[11 empty] | TXSHH-0502A/B (1oo2, SIL 1) high-high temp -> close UXV-0501/0502 (independent backup, C&E Cause 3) | Yes | 1
[11 empty] | PDAH-0301 filter high-dP DCS alarm + operator response | No | 1
1.2.1 | Flow | No / Low Flow | Spurious UC-2301 trip closes UXV-0401 with no real demand | Operability only — steam simultaneously isolated (safe direction for CHP); production interruption | 4 | 1 | 1 | 1 | 1 | Low | Procedural restart per startup SOP (HXS-0102 bypass) | No | 0 | 4 | 1 | 1 | 1 | 1 | Low | None — risk acceptable
2.1.1 | Flow | More Flow | OXI throughput increase / feed control upset -> higher oxidate mass flow | Reduced heat input per unit mass -> colder feed to V-2301 -> poorer cumene flash, off-spec concentration; no over-temperature hazard (safe direction). Production impact only | 3 | 1 | 1 | 2 | 1 | Low | FIC-0501 feed-forward steam control raises duty with flow | No | 1 | 2 | 1 | 1 | 2 | 1 | Low | None — risk acceptable (Ec: BU est. 0.1-<1M THB)
[11 empty] | Downstream V-2301 temperature/level/concentration controls | No | 0
3.1.1 | Flow | Reverse Flow | N/A — not credible: feed delivered under positive pump pressure from OXI; no credible downstream reversing source within node | — | [5 empty] | N/A | — | No | — | [5 empty] | N/A | None
4.1.1 | Temperature | More / High Temperature | E-2303 steam control fails to maximum heat input (FIC-0501/FXY-0501 malfunction or SC1.5 steam control valve fails open) | Oxidate heated above CHP decomposition onset (~80 C) -> autocatalytic exothermic decomposition in E-2303 and downstream -> overpressure, exchanger/piping rupture, LOPC of hot CHP -> fire/explosion, potential multiple fatalities | 4 | 5 | 4 | 5 | 4 | Extreme | TXSHH-0502A/B (1oo2, SIL 1) high-high oxidate temp -> UC-2301 closes UXV-0501/0502 (C&E Cause 3) | Yes | 1 | 2 | 5 | 4 | 5 | 4 | Medium | R-001
[11 empty] | TXAHN-0502 DCS critical high-temp alarm + operator cuts steam/trips | No | 1
[11 empty] | UXV-0501 + UXV-0502 redundant series SC1.5 steam isolation (final elements) | Yes | —
4.2.1 | Temperature | More / High Temperature | E-2302A/B shell-side hot OXI recirculate abnormally hot (upstream OXI temperature excursion) -> over-preheat of feed before E-2303 | Same CHP over-temperature / decomposition chain as 4.1.1, initiated on the preheat side -> rupture, fire/explosion | 3 | 5 | 4 | 5 | 4 | High | TXSHH-0501 (1oo1, SIL 1) high-high E-2302 oxidate outlet temp -> UC-2301 ESD (C&E Cause 2) | Yes | 1 | 1 | 5 | 4 | 5 | 4 | Low | None at node level — confirm TXSHH-0501 setpoint margin under R-001
[11 empty] | TXAHN-0501 DCS critical alarm + operator | No | 1
[11 empty] | OXI section temperature control / OXI ESD cross-trip UC-2201 -> UC-2301 (C&E Cause 12) | Yes | 1
5.1.1 | Temperature | Less / Low Temperature | Loss of SC1.5 steam (header loss, UXV-0501/0502 spurious close, FIC-0501 fails low) and/or loss of E-2302 preheat (OXI recirculate cold/lost) | Cold feed to V-2301 -> poor cumene flash, off-spec concentration, column upset, production loss. Safe direction for CHP. Possible un-concentrated CHP carry-forward needing downstream management | 4 | 1 | 1 | 2 | 1 | Medium | TI/TT-0505 temperature indication + control | No | 1 | 3 | 1 | 1 | 2 | 1 | Low | None — residual Low after operator response; Economic (Ec 2) to be validated by team
[11 empty] | Downstream V-2301 controls and concentration analyzers | No | 0
6.1.1 | Pressure | More / High Pressure | Process (CHP) side blocked in (e.g. isolated for maintenance with residual CHP) with a heat source present (steam not isolated, fire, or decomposition) -> thermal expansion / decomposition-gas pressurisation of liquid-full exchanger | Process-side overpressure beyond E-2302 tube (12) / E-2303 shell (3.5 FV) rating -> exchanger rupture -> LOPC of CHP -> fire/explosion | 3 | 5 | 4 | 5 | 4 | High | Normal lineup: process side open to V-2301, relieves via PSV-23-0401A/B/C/D (set 2.10/2.205 kg/cm2g, DIERS runaway case) | No | 2 | 2 | 5 | 4 | 5 | 4 | Medium | R-003
[11 empty] | High-temp SIFs (TXSHH-0501 / TXSHH-0502A/B) cut heat source before decomposition pressure develops | Yes | 1
[11 empty] | GAP: no dedicated PSV on E-2302A/B / E-2303 process side when block-isolated from V-2301 relief | No | 0
6.2.1 | Pressure | More / High Pressure | SC1.5 steam supply overpressure into E-2303 tube / condensate system (steam header excursion) | Steam-side (tube 7, D-2308 7 kg/cm2g) overpressure -> tube/drum overpressure -> LOPC of steam/condensate (low chemical hazard); possible escalation to process side via tube failure (#11.1) | 3 | 2 | 1 | 2 | 1 | Low | PSV-23-0501 on D-2308 (set 7.0 kg/cm2g, fire case, 157 kg/h) protects condensate/tube circuit | No | 2 | 1 | 2 | 1 | 2 | 1 | Very Low | Confirm PSV-23-0501 also bounds steam-supply overpressure case (note under R-003)
7.1.1 | Pressure | Less / Vacuum | Steam-side vacuum on trip — sudden steam isolation (UXV-0501/0502 close) collapses steam in E-2303 tubes -> vacuum / condensate-induced water hammer | Vacuum collapse / water hammer in E-2303 tube bundle -> tube mechanical damage -> progression to tube leak (#11.1) | 3 | 2 | 1 | 2 | 1 | Low | E-2303 tube bundle rated for Full Vacuum (design FV); D-2308 design FV (inherent design) | No | — | 2 | 2 | 1 | 2 | 1 | Low | Confirm no vacuum-breaker requirement given FV-rated design
8.1.1 | Level | More / High Level (D-2308) | LIC-0502 / LV-0502 condensate return control fails closed, or condensate return header backpressure -> D-2308 level rises | Condensate backs up into E-2303 tube bundle -> flooding -> loss of steam heat-transfer area -> erratic/low feed temperature to V-2301 (links #5.1); potential condensate-induced water hammer | 4 | 2 | 1 | 2 | 1 | Medium | LAH-0502 high-level DCS alarm + operator; HLL 740 mm reference | No | 1 | 3 | 2 | 1 | 2 | 1 | Low | None — risk acceptable
[11 empty] | LIC-0502 level control loop | No | 0
9.1.1 | Level | Less / Low Level (D-2308) | Excess condensate pump-out / loss of condensate make (steam off) / LV-0502 fails open -> D-2308 level falls | P-2308A/B lose suction (NPSH) -> cavitation / steam blow-through to condensate return system; possible pump damage | 4 | 2 | 1 | 2 | 1 | Medium | LAL-0502 low-level alarm + operator; LLL 260 mm reference | No | 1 | 3 | 2 | 1 | 2 | 1 | Low | None — consider LALL/auto-stop on D-2308 to protect P-2308 (operability, defer to team)
[11 empty] | P-2308 sealless mag-drive (no seal leak path) | No | 0
10.1.1 | Service Failures | Loss of Utility — Power | Loss of electrical power -> P-2308A/B both stop (Type L, not on reliable power) | Condensate accumulates in D-2308 -> backs into E-2303 (as #8.1.1) -> low/erratic feed temperature; no direct CHP hazard | 4 | 2 | 1 | 2 | 1 | Medium | LAH-0502 high-level alarm + operator | No | 1 | 3 | 2 | 1 | 2 | 1 | Low | None
[11 empty] | UC-2301 ESD on associated trips removes SC1.5 steam | Yes | 1
10.2.1 | Service Failures | Loss of Utility — Instrument Air | Loss of instrument air -> SC1.5 steam control valve (FV-0501) and LV-0502 go to fail position | If steam valve fails OPEN -> High Temperature (refer #4.1.1, CHP decomposition). If fails CLOSED -> Low Temperature (refer #5.1.1). Outcome depends on fail-action (to confirm) | [5 empty] | N/A | ACTION: confirm fail-safe action of FV-0501 and LV-0502 (control-valve register) | No | — | [5 empty] | N/A | Confirm fail-safe actions (note under R-003); refer #4.1.1 / #5.1.1
11.1.1 | Composition / As Well As | Tube Leak / Rupture (E-2303) | E-2303 tube leak/rupture between SC1.5 steam (tube) and oxidate (shell, CHP) | Process oxidate (~8 kg/cm2g) leaks into lower-pressure steam-condensate side -> CHP migrates to the steam-condensate system (D-2308 -> condensate return 66-0056), which is NOT rated/monitored for CHP -> uncontrolled CHP in a utility system, off-site migration, potential decomposition/fire; conversely water/steam ingress contaminates the CHP oxidate | 3 | 4 | 3 | 4 | 3 | High | 304L SS tubes (corrosion resistant to CHP) | No | 0 | 3 | 4 | 3 | 4 | 3 | High | R-002
[11 empty] | Construction-stage helium leak test (one-time, not an operating IPL) | No | 0
[11 empty] | Periodic inspection (non-IPL per Table 6.6). NOTE: no on-line CHP/HC detection on D-2308 condensate identified | No | 0
11.2.1 | Composition / As Well As | Tube Leak / Rupture (E-2302A/B) | E-2302A/B tube leak/rupture between fresh oxidate (tube, 12 kg/cm2g) and hot OXI recirculate (shell, 3.5 FV) | HP tube side leaks to LP shell side -> shell overpressure; both fluids CHP-containing (lower contamination concern) but pressure differential and CHP inventory mixing. Relief via shell-side / V-2301 system | 3 | 3 | 3 | 3 | 2 | Medium | 304L SS tubes; helium leak test at construction | No | 0 | 2 | 3 | 3 | 3 | 2 | Low | None — confirm shell-side overpressure relief adequacy under R-003
[11 empty] | Shell-side relief path to OXI / column system | No | 2
[11 empty] | High-temp SIFs limit escalation | Yes | 1
12.1.1 | Composition | Other Than (Contamination) | Iron/transition-metal or acid contamination of the CHP oxidate (corrosion products, upstream carryover) — potent CHP decomposition catalysts | Catalysed CHP decomposition at lower temperature than expected -> localized exotherm -> as #4.1.1 (rupture, fire/explosion) | 2 | 5 | 4 | 5 | 4 | Medium | 304L SS wetted parts throughout (no Cu/Cu-alloy, no carbon steel in CHP service) | No | 1 | 1 | 5 | 4 | 5 | 4 | Low | None — confirm condensate/contamination monitoring under R-002
[11 empty] | X-2302 feed filters remove particulates upstream (Node 23-01) | No | 0
[11 empty] | High-temp SIFs (TXSHH-0501/0502) | Yes | 1

## Action Items
No. | Node | Deviation Ref | Action item detail | Risk Rank | Discipline | Owner Type | Responsible (Emp ID / Name or External) | Due Date | Action Approver | Completion Date | Approved Date | Status
R-001 | CDN-N02 | #1.1.1, #4.1.1 | Perform LOPA / SIF verification confirming combined overheat protection (TXSHH-0501 SIL 1 + TXSHH-0502A/B SIL 1 + redundant UXV-0501/0502) achieves tolerable risk for the S5 CHP-decomposition consequence; confirm all TXSHH setpoints sit below the 80 C onset with adequate margin; confirm startup bypass HXS-0102 does not disable temperature protection. | Medium | Instrument / Process | TBD | TBD | TBD | TBD |  |  | Open
R-002 | CDN-N02 | #11.1.1 | Provide on-line detection of CHP/hydrocarbon carryover into the steam-condensate system (conductivity/pH or HC analyzer with alarm and/or condensate divert) at D-2308 / condensate return, to detect an E-2303 tube leak and prevent CHP migration to the unrated utility condensate system. | High | Process / Instrument | TBD | TBD | TBD | TBD |  |  | Open
R-003 | CDN-N02 | #6.1.1, #11.2.1 | Review overpressure/thermal-relief protection for E-2302A/B and E-2303 process (CHP) side when block-isolated for maintenance (no dedicated PSV once isolated from V-2301 relief); confirm safe CHP draining/purging for single-train isolation; confirm steam control valve fail-action. | Medium | Process / Mechanical | TBD | TBD | TBD | TBD |  |  | Open
R-004 | CDN-N02 | Normal Params / #6 | Resolve the oxidate feed pressure data conflict (S229 78 kg/cm2G vs E-2302 tube 12 / X-2302 8 kg/cm2g) and confirm feed-line design pressure / piping class. | Low | Process | TBD | TBD | TBD | TBD |  |  | Open

## Risk Ranking
PHA RISK MATRIX (W-(Q-MP)-002 R2) — highest of P/En/Ec/S sets the severity
Likelihood \ Severity | S1 Very Low | S2 Low | S3 Medium | S4 High | S5 Extreme
L5 Frequent | Low | Medium | High | Extreme | Extreme
L4 Likely | Low | Medium | High | High | Extreme
L3 Possible | Low | Low | Medium | High | High
L2 Unlikely | Very Low | Low | Low | Medium | Medium
L1 Improbable | Very Low | Very Low | Low | Low | Low
Action thresholds: Extreme/High -> action & risk reduction plan immediately; Medium -> require risk reduction plan; Low -> review control plan; Very Low -> no action.
Economic category for PPCL = BU: Extreme >=100M; High 10-<100M; Medium 1-<10M; Low 0.1-<1M; Very Low <0.1M THB.
Likelihood: L5 >1/yr at location; L4 at location or >1/yr in group; L3 in group or >1/yr industry; L2 possible in industry; L1 unlikely in industry.
Severity fixed between Without/With safeguard; only Likelihood changes with IPLs (SIL1 -1 level, SIL2 -2).

## Interlock-ESD Summary
Existing Safeguard (IL/ESD) | Node | Possible Cause | Potential Consequence | WO L | WO P | WO En | WO Ec | WO S | WO RR | W L | W P | W En | W Ec | W S | W RR
FXSLL-0401A/B/C (2oo3, SIL 1) -> UC-2301: close UXV-0401 feed + UXV-0501/0502 steam (C&E Cause 1) | CDN-N02 | Loss of oxidate feed (filter plug / OXI pump trip / UXV-0401) with steam on | Stagnant CHP overheats in E-2303 -> decomposition -> rupture, fire/explosion | 4 | 5 | 4 | 5 | 4 | Extreme | 2 | 5 | 4 | 5 | 4 | Medium
TXSHH-0501 (1oo1, SIL 1) -> UC-2301 Concentration ESD (C&E Cause 2) | CDN-N02 | E-2302A/B hot OXI recirculate over-temperature (preheat) | CHP over-temperature -> decomposition -> rupture, fire/explosion | 3 | 5 | 4 | 5 | 4 | High | 1 | 5 | 4 | 5 | 4 | Low
TXSHH-0502A/B (1oo2, SIL 1) -> UC-2301: close UXV-0501/0502 SC1.5 steam (C&E Cause 3) | CDN-N02 | E-2303 steam control fails open (FIC-0501 / valve) | CHP over-temperature -> decomposition -> rupture, fire/explosion | 4 | 5 | 4 | 5 | 4 | Extreme | 2 | 5 | 4 | 5 | 4 | Medium
UXV-0501 + UXV-0502 redundant series SC1.5 steam isolation (UC-2301 final elements) | CDN-N02 | Any UC-2301 demand (above causes) | Positive removal of heat source from CHP-containing oxidate | WO RR: (final element)